## Overview Pivot
Row Labels | Count of Rank
Product | 8
Major | 3
Moderate | 5
Product-Specific | 3
Moderate | 3
Project | 9
Major | 3
Moderate | 5
Severe | 1
Grand Total | 20
Product Specific : Product-specific risks can be distinguished from generic risks because they can only be identified by those with a clear understanding of the technology, the people, and the environment of the specific product.
Product: Product risks are those that affect the quality or performance of the software being developed.
Project : Project risks are those that affect the project schedule or the resources (personnel or budgets) dedicated to the project.

## Data
Rank | Prev Rank | Risk | Category | Probability | Impact | Owner | Mitigation
1 | 1 | Given that we may be over optimistic about deadlines there is a concern that tasks will overrun resulting in varying delays meaning we may have to reevaluate requirements. | Product | Major | Likely | Scrum Master | Set artificial deadlines Frequent Meetings Online Communication | Amber
2 | 2 | Given that throughout the project the customer requirements may change, there is a concern that we will not be able to fully satisfy all of the requested changes leaving the customer unsatisfied. | Project | Moderate | Possible | Product Owner | Frequent meetings between development team and customer Early artificial deadlines Online communication with the customer | Yellow
3 | 3 | Given that the team may have a varying skill sets there is a concern that individuals may be allocated tasks that they are not suited for meaning the quality of the product may suffer. | Project | Major | Likely | Scrum Master | Implementation of pair programming Frequent communication between developers Regular peer reviews of work | Amber
4 |  | Given that the team has to work with unknown code there is a concern that the additional workload required to understand it will delay the work | Product-Specific | Minor | Likely | Scrum Master | Regular Meetings, Regular reviews of the code. Assigning two architects to manage the transition. | Yellow
5 |  | Given that we are now working with code written by another team there is a chance that it might not function as advertised. | Product-Specific | Severe | Likely | Scrum Master | Regular Meetings, Regular reviews of the code. Assigning two architects to manage the transition. | RED
6 | 4 | s | Project | Moderate | Likely | Scrum Master | Compulsory meetings Artificial deadline Online communication | Amber
7 | 5 | Given that there may be misunderstanding between the teams members there is a concern that tasks will be inadequately completed meaning extra time must be used to fix any issues. | Product | Moderate | Almost Certain | Scrum Master | Regular meetings Short development cycles Communication channels for task assignment | Amber
8 | 6 | Given that with the Agile methodology there is no clear hierarchy there is a concern that the decision making process will take longer than necessary. | Product | Moderate | Likely | Scrum Master | Pick specialists for different tasks Voting / team discussions Go to customer if design decision | Amber
9 | 7 | Given that the timeline for this projects spans over weekends and Christmas holidays there is a concern that team members will stop working during those periods and a such work may not be completed on time. | Product | Major | Possible | Scrum Master | Regular meetings (online or in person) Progress reviews Artificial deadline | Amber
10 | 8 | Given that engineers are keen to display their skills there is a concern that large amounts of time may be spent implementing unnecessary features meaning that core functionality may not be developed fully | Product | Moderate | Likely | Scrum Master | Design reviews Strict task assignment Customer involvement | Amber
11 | 9 | Given that there is a chance a team member may have mitigating circumstances and take a leave of absence from university there is a concern that the team will not have sufficient members to complete the project to the specified time period and quality | Project | Severe | Rare | Risk Maneger | Assigning more than one person per task Online communication Regular reviews by the group | Amber
12 |  | Given that we are now working in 3d there is a concern that team members might not be able to work with 3d graphics resulting in delays. | Product | Moderate | Possible | Product Owner | Limit the use of 3D models in critical applications | Yellow
13 | 10 | Given that we are working as a team on the same project and documents there is a concern that work could be lost or damaged in the document exchange phase, leading to reduced productivity. | Project | Major | Possible | Librarian | Version control systems Online backup tools such as Google Drive | Amber
14 | 11 | Given that the client’s requirements may change there is a concern that new or vastly different requirements may be introduced after the design phase leading to a large loss of work. | Product | Major | Possible | Product Owner | Frequent meetings between development team and customer Early artificial deadlines Online communication with the customer | Amber
15 | 12 | Given that the city of York lies on a floodplain there is a concern that hardware that we are using is either inaccessible or damaged which may lead to loss of work and/or work not being completed on time. | Project | Major | Possible | Risk Maneger | Online tools Early artificial deadlines Online communication with the customer | Amber
16 | 13 | Given that engineers may lose motivation through the project there is a concern that the work will take longer than estimated meaning that some functionality may not be implemented. | Project | Moderate | Possible | Scrum Master | Artificial deadline Team building activities Variety of tasks given to each team member | Yellow
17 | 14 | Given that team members have different personalities there is a concern that some of them may not get their say in group discussions meaning some ideas are never discovered. | Project | Moderate | Possible | Scrum Master | Meetings with group participation techniques Brain showers Small group work & feeding back to the rest of the team | Yellow
18 | 15 | Given that we have to take on another team's product there is a concern that we may find it difficult to understand how their product works, due to the technology used or bad documentation, meaning more time is spent researching how it works. | Product-Specific | Moderate | Possible | Risk Maneger | Contact the team Review the project as a team Research the project before picking it | Yellow
19 | 16 | Given that contact with the client may not always be possible there is a concern that we may implement features that were not confirmed by the client or development may be delayed. | Product | Moderate | Unlikely | Product Owner | Frequent meetings with customer Online communication Implement only confirmed features | Yellow
20 | 17 | Given that the design stage is complex and time constrained there is a concern that there will be unnecessary compromises made meaning that the overall product may not be effectively designed to the specification | Product | Moderate | Possible | Scrum Master | Talk to customer about design | Yellow
21 | 18 | Given that we are required to swap projects with another team there is a risk that the work taken will be lacking in quality or direction meaning that we may have to spend more time than is desirable to further develop the solution to a high standard | Product-Specific | Moderate | Possible | Risk Maneger | Contact the team Review the project as a team Research the project before picking it | Yellow
22 | 19 | Given that we may be working with different technologies such as operating systems there is a concern that software developed by one member may not be able to be used by another team member, leading to a disjointed and ineffective solution. | Product-Specific | Moderate | Possible | Risk Maneger | Pick platform independent technology Online tools such as google drive | Yellow
23 | 20 | Given that individuals have other commitments outside of the project there is a concern that an individual may rest inadequately or experience burnout meaning that they are not as motivated or able to perform well. | Project | Moderate | Likely | Scrum Master | Risk acceptance : acknowledge the risk. Managing the size of each individual's workload Having clear goals Encouraging regular exercise. | Amber