## Sheet1
ID | Objective | Description | Expected Result | Actual Result
I1 | Check Networking between two clients | Connect two clients using the LAN Host option on one and LAN Client on the other | The two clients connect and gameplay starts | Two clients connect and gameplay starts
I2 | Check that Tiles update across clients when roboticon placement occurs | Purchase a tile and place a roboticon on one client. | When one client purchaces land and places a roboticon the roboticon appears on the other client's screen | When one client purchaces land and places a roboticon the roboticon appears on the other client's screen
I3 | Check that market variables update across clients | Have both clients buy and sell to the market | Both client's market UI update according to the changes. | Both client's market UI update according to the changes.
I4 | Check that the phase ends once the timer is completed | Let the timer time out, observe result. | Timer times out, next phase for other player initiated. | Timer times out, client defaults to roboticon placement instead of forefiting turn. | now fixed
I5 | Check recource depletion works | Check that the aquired amount of a resource is subtracted from the tile value of a resource | The resource value on the tile is subtracted the amount of resource which is gained by the roboticon | The resource value on the tile is subtracted the amount of resource which is gained by the roboticon